## Sheet1
ST CLARE'S RC PRIMARY SCHOOL
SCHOOL IMPROVEMENT PLAN 2019-20
OUR VISION
Guided by Jesus Christ, our teacher, we journey together, learning to dream, believe and achieve.
|  | Focus: Quality of Education |  | Focus: Quality of Education |  | Focus: Leadership and Management |  | Focus: Personal Development | Focus: Early Years
|  | Strategic Objective |  | Strategic Objective |  | Strategic Objective |  | Strategic Objective | Strategic Objective
|  | Improve standards in the wider curriculum |  | Reduce gaps in attainment |  | Improve subject leadership |  | Improve SMSC | Improve boys' attainment
St Clare's RC Primary School
Strategic Objective 1: Improve standards in the wider curriculum
Terms |  |  | Milestones
End of Autumn |  |  | Subject leaders have a long-term map in place for their subjects
End of Spring |  |  | All subjects are properly sequenced
End of Summer |  |  | Assessment arrangements in place for each subject
Objective |  | Milestones |  |  | Lead | Timescale | Cost | Impact | Evaluation
1.1 Improve the sequencing and assessment of each subject. |  | Long-term overview for the whole curriculum. |  |  | SLT | Dec '19 | 2000 | Clearer progression and end points in each year | Discussions with pupils
|  | Knowledge mats and key questions in place for each subject |  |  | Sub leaders | April '20 | 500 | Improved impact of assessment | Audit of plans
|  | Assessment clear in each subject |  |  | Sub leaders | June '20 | 2000 | Clearer expectations in each year group
|  | Curriculum clear on the website |  |  | Sub leaders | June '20 | 0
1.2 Embed key drivers in curriculum provision. |  | Quality texts linked to topics |  |  | Lit lead | Feb '20 | 2000 | Improved focus on language and reading | Audit of plans and book scrutiny
|  | Age-related texts in place for each subject |  |  | Lit lead | June '20 | 5000 | Stronger language focus in each classroom. | Lesson observations
|  | Broader oppportunities mapped by year |  |  | Teachers | June '20 | 10000 |  | Review of non-negotiables in classes
|  | Drivers evident in class rooms |  |  | SLT | April '20 | 2000 | Intent links to curriculum design
|  | Revise intent statement for 2020 |  |  | Teachers | June '20 | 0 |  | Statement revision
1.3 Improve assessment in each subject |  | Expectations for assessing each subject in a new policy |  |  | SLT | Jan '20 | 0 | Assessment expecatations clear | Discussions with pupils and teachers
|  | Staff skilled in formative assessment |  |  | SLT | Mar '20 | 200 | Improved, more consitent assessment evidenced in amended teaching | Evidence trails
|  | Effective medium-term assessments |  |  | Sub leaders | April '20 | 0 |  | Review of books
|  | Links with above to amended teaching |  |  | Teachers | April '20 | 0
St Clare's RC Primary School
Strategic Objective 2: Reduce gaps in attainment
Terms |  |  | Milestones
End of Autumn |  |  | Improved link between planning and assessment
End of Spring |  |  | Improved targeting of pupils
End of Summer |  |  | Improved teaching in maths and science
Objective |  | Milestones |  |  | Lead | Timescale | Cost | Impact | Evaluation
2.1 Improve outcomes in KS2 Science |  | Clearer sequencing and end points |  |  | Science lead | April '20 | 0 | More open-ended learning and better language development | Discussion with pupils
|  | Reading supporting learning in all classes |  |  | Science lead | April '20 | See obj 1 |  | Review of teacher records
|  | Good formative assessment to establish issues |  |  | SLT | Feb '20 | 0 |  | Observation of TAs
|  | Pace ensures catch-up for targeted pupils |  |  | SLT | Feb '20 | 0 | Better targeting and outcomes in line with national | Observation of HT assessments
|  | TAs used for pre-teaching in KS2 |  |  | SLT | Dec '20 | 0 |  | Discussion with teachers
|  | Strategies for reflecting on learning |  |  | SLT | Feb '20 | 0
2.2 Improve attainment in maths |  | Maths audit |  |  | Focus | Dec '19 | 2000 | Improved targeting and provision leading to attainment in that is in line with national in all year groups | Audit
|  | Improve formative assessment |  |  | CMc | Mar '20 | 0 |  | Books
|  | Practical equipment in all classes |  |  | Maths lead | Dec '19 | 500 |  | Discussions with staff
|  | Improved targeting of pupils |  |  | SLT | Feb '20 | 0 |  | Discussions with pupils
Review of data
2.3 Improve boys' progress in KS1 and KS2 |  | Audit of boys' views on their learning |  |  | C.S & J.O'K | 2019-11-01 | 0 | Improved disposition of boys to learning. Improved outcomes for boys. Improved motivation in boys. Increased number of strategies to regulate emotions. Improved boys engagement. | Discussions with boys and review of their work. Review of relevant intervention programmes and pilots within each year group.
|  | In Year 5 and 2 pilot seating: pair girls next to boys. Girls to encourage boys how to listen well. |  |  | Y5&2 teachers | 2019-11-01 | 0
|  | In Year 5 and Year 2 pilot Yoga and Meditation as a relaxation strategy. |  |  | Y5&2 teachers | 2020-01-01 | 3000
|  | In Year 6 pilot pupils learning to teach and assess themselves. To be more independent, monitor their own targets. |  |  | Y6 teachers | 2020-01-01 | 0
|  | In Year 6 pilot pupils being given opportunities to discuss, demonstrate and be active participation. |  |  | Y6 teachers | 2020-01-01 | 0
|  | In Year 4RW pilot Emotional Literacy programme and modelling |  |  | 4RW | 2019-11-01 | 100
|  | Throughout KS2 negotiate acceptable movement rather than insisting that boys stay seated. |  |  | KS2 teachers | 2019-11-01 | 0
|  | Introduce motivational Reward system across school for progress/achievement in core subject areas. Rewards to include…football coaching sessions, football memorabilia, games, lego |  |  | C.S & J'O'K | 2020-03-01 | 5000
St Clare's RC Primary School
Strategic Objective 3: To improve subject leadership
Terms |  |  | Milestones
End of Autumn |  |  | All leaders have a subject statement of intent that reflects the school's five drivers
End of Spring |  |  | Subject learning challenges and knowledge mats are directly linked to the subject intent
End of Summer |  |  | Subject monitoring diary in place for 2020-21
Objective |  | Milestones |  |  | Lead | Timescale | Cost | Impact | Evaluation
3.1 The school's main drivers are evident in the expectations in each subject. |  | Subject leaders understand 5 main drivers |  |  | SLT | Nov '19 | 0 | 5 main drivers of faith, community, language, opportunity and curiosity are clear in the intent for each subject. | Statements of intent on the school website
|  | Subject leaders understand the purpose of study for their subject in the NC |  |  | SLT | Nov '19 | 0
|  | Subject leaders produce their statement of intent for their subject |  |  | Teachers | Nov '19 | 0
|  | Final audit of each statement against the 5 main drivers. Added to website page |  |  | SLT | Nov '19 | 0
3.2 The curriculum for each subject is securely linked to the subject statement of intent. |  | SLT work with subject leaders on overarching question for each topic |  |  | SLT | Dec '19 | 0 | The intent in each subject, beyond the NC, is embedded in publicised plans. | Audit of curriculum plans in all subjects
|  | Subject leaders complete key knowledge and learning for each topic |  |  | Sub leaders | Feb '20 | 0
|  | SLT and staff audit curriculum plans against statements of intent (5 drivers) |  |  | SLT | Feb '20 | 0
3.3 Subject leaders know how to monitor their subjects effectively |  | Subject leaders know they are not just monitoring against the NC |  |  | SLT | March '20 | 0 | Exemplification, statements of intent and effective training ensure that monitoring adds to a cycle of continuous improvement. | Discussions with subject leaders
|  | Every subject leader is trained to monitor effectively |  |  | SLT | May '20 | 0 |  | Review of monitoring strategies
|  | Working with the SLT, every subject leader has a written monitoring diary/strategy |  |  | SLT | July '20 | 0
St Clare's RC Primary School
Strategic Objective 4: Improve SMSC
Terms |  |  | Milestones
End of Autumn |  |  | Pupils are more independent
End of Spring |  |  | Improve provision for character development
End of Summer |  |  | Pupils' have a stronger understanding of British values
Objective |  | Milestones |  |  | Lead | Timescale | Cost | Impact | Evaluation
4.1 Improve pupils' independence |  | Discussion with teachers | [5 empty] | Pupils are more aware of independence issues and are more proactive in their response. | Learning walks to classrooms to observe levels of independence in lessons.
Audit pupils' views and understanding
|  | Identify key indpendence targets |  |  | SLT | Jan | 0
|  | Develop a progression of independent skills - to prepare for next key-stage |  |  | SLT | Jan | 0
|  | Share progression with parents |  |  | SLT | Feb | 0
|  | Child-led collective worship |  |  | RM | Mar | 200
|  | Pupils at Y5/6 teach and mentor |  |  | RH | Mar | 100
4.2 Improve pupils' understanding of character development and respect for others |  | Research philosophy for children |  |  | RH | Feb | 200 | Pupils reflect on broader developmental issues and understand the need for respect even when disagreeing on an issue with others. | Discussions with pupils and observations of debates.
|  | Share the above with the staff |  |  | RH | Apr | 0
|  | Build debating into currriculum topics |  |  | SLT | May | 0
|  | Pupils know protocols on respectful debating |  |  | Teachers | May | 0
|  | Deliver the Happiness project to Year 6 over 10 weeks. |  |  | SLT | Jan | 1600
4.3 Improve pupils' understanding of citizenship and community responsibilities |  | Introduce assemblies led by Eco Warriors, Chaplains and Pupil Council. Introduce sports leaders. Assemblies by digital leaders and science ambassadors. |  |  | Teachers | Dec | 200 | Pupils have a greater role within their school and local community and understand the value of this and how it links to their faith. | Observation of assemblies. Discussions with pupils. Observation of work with the elderly in the community.
|  | Improve discrete teaching on on liberty, justice and democracy |  |  | JH | Jan | 200
|  | Visits to groups within the community |  |  | SLT | June | 300 | Improved understanding of issues linked to liberty, democracy and justice
|  | Pupil-led coffee morning |  |  | SLT | Mar | 200
St Clare's RC Primary School
Strategic Objective 5: To improve boys' attainment in EYFS
Terms |  |  | Milestones
End of Autumn |  |  | Strategies are securely in place for improving boys outcomes in EYFS
End of Spring |  |  | Interventions and support strategies for pupils are at least good in all areas and classes
End of Summer |  |  | Strategies for language development are clearly evident in curriculum design
Objective |  | Milestone |  |  | Lead | Timescale | Cost | Impact | Evaluation
To create an enabling Early Years curriculum and learning environment that that provides a rich, varied and imaginative experiences and meets the needs of all learners. |  | TAs to be effective in facilitating children’s learning during child initiated and in questioning children |  |  | CMcG | Jan | 0 | A stimulating EYFS environment that motivates learning. Ensure good transition routines are in place- no lost learning time. | Discussion with pupils. Review of learning journeys. Discussion with staff.
|  | Review timetable arrangements to ensure time is used effectively to raise attainment |  |  | EYFS team | Dec | 0
|  | Nursery and Reception to plan for outdoor provision together, with a focus on gross and fine motor skills |  |  | EYFS Team | Dec | 0
|  | Commission EYFS (EY2P) review to support induction of a new team of staff and to ensure development of high quality provision. (2 days support - spring/ Summer) |  |  | CMcG | Spring/ Sum | 1200
|  | Purchase the Firm Foundations Numicon Folder and boards to develop and enhance teaching and learning. |  |  | CMcG | Nov | 120
|  | Emphasis on kinaesthetic activities in planning for boys (indoor and outdoor) to understand concepts (ongoing). Outdoor clothing to be purchased. |  |  | CMcG | Nov | 1500
Implement strategies for promoting oracy and extending vocabulary, e.g. Welcom/ Tales Toolkit/ word aware. To close the gap of highlighted vulnerable groups through targeted intervention in these areas. |  | Continuous provision activities based around oracy/ Word aware activities in teaching (obtain materials) |  |  | EYFS Team | Dec | 100 | Increased vocabulary to aid with reading and writing. Engagement of parents and carers in their children’s learning in school and at home. | Discussion with pupils. Review of learning journeys. Discussion with staff. Learning walks.
|  | Daily 'welcom' activity to be taught whole class/ |  |  | EYFS Team | Oct | 0
|  | Welcom assessment to be carried out and TA led interventions used based on outcomes/ / |  |  | EYFS Team | Oct | 0
|  | To give support in small group work for listening and speaking skills. Tales toolkit to be used in whole class teaching. |  |  | EYFS Team | Mar | 800
|  | To highlight target children across EYFS for GLD ensuring our assessment procedures are robust and accurate through regular moderation with our collaboration school and other local schools and EY2P (2 days support spr/ sum) |  |  | CMcG | May | 0
|  | To give support in PSED-using social circles group work to enable turn taking and sharing |  |  | EYFS Team | Jan | 0
|  | To continue to embed parental involvement through workshops, information evenings and stay with your child events/ (Autumn focus on language and oracy) |  |  | EYFS Team | Nov | 0
Implement strategies for promoting physical development, e.g. Balance Bikes/ outdoor learning activities.To close the gap of highlighted vulnerable groups through targeted intervention in these areas. |  | Continuous provision activities based around Physical Development with a focus on Moving and Handling and fine motor skills (needed for writing) |  |  | EYFS Team | Dec | 0 | Improved motor control (needed for writing). Engagement of parents and carers in their children’s learning in school and at home. | Discussion with pupils. Review of learning journeys. Discussion with staff. Learning walks.
|  | Introduction of regular balance bike activities ( Baalnce bike to be purchadsed and staff trined on their use) |  |  | HB/ CmcG | Feb | 700
|  | To give support for fine motor skills by small group work ‘funky fingers’ to develop finger muscles to help children hold writing implements correctly/ |  |  | EYFS Team | Dec | 0
|  | To highlight target children across EYFS for GLD ensuring our assessment procedures are robust and accurate through regular moderation with our collaboration school and other local schools and EY2P |  |  | CMcG | Nov | 0
|  | To continue to embed parental involvement through workshops, information evenings and stay with your child events/ (Stay and play focus on Moving and handling) Spring. |  |  | EYFS Team | Feb | 0